## total
MM_trained | PBFW | Children | PBFW_cell | Children_cell | Total_VMM | Pre_consent | Refusals
278 | 16390 | 1562 | 5966 | 597 | 6563 | 5643 | 5

## dataprov_12
province | PBFW | CHILDREN | ELEGIBLE
Cabo Delgado | 339 | 73 | 412
Gaza | #N/A | #N/A | #N/A
Inhambane | #N/A | #N/A | #N/A
Manica | #N/A | #N/A | #N/A
Maputo | 777 | 44 | 821
Maputo City | #N/A | #N/A | #N/A
Nampula | 2568 | 333 | 2901
Niassa | #N/A | #N/A | #N/A
Sofala | #N/A | #N/A | #N/A
Tete | #N/A | #N/A | #N/A
Zambezia | 2282 | 147 | 2429

## enrolled_pct
province | PBFW | children | phone
Cabo Delgado | 54 | 44 | yes
Nampula | 42 | 32 | yes
Zambezia | 26 | 46 | yes
Matola-II | 94 | 83 | yes
Cabo Delgado | 46 | 56 | no
Nampula | 58 | 68 | no
Zambezia | 74 | 54 | no
Matola-II | 6 | 17 | no

## weeks
week | Cabo_Delgado | Nampula | Zambezia | Matola | m2m | call
May-08 | 99 | 2020 | 1656 | 602 | 4377 | pre
May-15 | 99 | 2086 | 1744 | 603 | 4532 | pre
May-22 | 109 | 2205 | 1841 | 636 | 4791 | pre
May-29 | 112 | 2265 | 1910 | 688 | 4975 | pre
June-05 | 145 | 2270 | 1965 | 711 | 5091 | pre
June-12 | 171 | 2342 | 2017 | 740 | 5270 | pre
June-19 | 190 | 2382 | 2079 | 752 | 5403 | pre
June-26 | 194 | 2397 | 2097 | 752 | 5440 | pre
July-03 | 206 | 2422 | 2125 | 752 | 5505 | pre
July-10 | 206 | 2461 | 2178 | 798 | 5643 | pre
May-08 | 94 | 1452 | 1242 | 280 | 3068 | first
May-15 | 94 | 1452 | 1403 | 547 | 3496 | first
May-22 | 104 | 2059 | 1403 | 587 | 4153 | first
May-29 | 110 | 2185 | 1498 | 649 | 4442 | first
June-05 | 131 | 2201 | 1579 | 692 | 4603 | first
June-12 | 141 | 2236 | 1676 | 720 | 4773 | first
June-19 | 153 | 2290 | 1728 | 750 | 4921 | first
June-26 | 175 | 2318 | 1799 | 750 | 5042 | first
July-03 | 189 | 2316 | 1790 | 750 | 5045 | first
July-10 | 200 | 2371 | 1904 | 777 | 5252 | first
May-15 | 63 | 990 | 1387 | 410 | 2850 | second
May-22 | 92 | 1218 | 1387 | 488 | 3185 | second
May-29 | 104 | 1780 | 1429 | 488 | 3801 | second
June-05 | 119 | 1824 | 1503 | 625 | 4071 | second
June-12 | 127 | 2051 | 1598 | 691 | 4467 | second
June-19 | 145 | 2120 | 1677 | 698 | 4640 | second
June-26 | 160 | 2150 | 1743 | 698 | 4751 | second
July-03 | 176 | 2157 | 1758 | 728 | 4819 | second
July-10 | 198 | 2313 | 1849 | 738 | 5098 | second
May-22 | 26 | 104 | 733 |  | 863 | third
May-29 | 78 | 414 | 733 | 100 | 1325 | third
June-05 | 106 | 1285 | 1367 | 286 | 3044 | third
June-12 | 124 | 1853 | 1409 | 500 | 3886 | third
June-19 | 139 | 2068 | 1481 | 653 | 4341 | third
June-26 | 149 | 2143 | 1587 | 653 | 4532 | third
July-03 | 174 | 2192 | 1587 | 689 | 4642 | third
July-10 | 186 | 2313 | 1814 | 711 | 5024 | third
May-08 | 75 | 62 | 27 | 71 | 44 | drug
May-15 | 80 | 61 | 34 | 71 | 47 | drug
May-22 | 80 | 63 | 40 | 71 | 51 | drug
May-29 | 82 | 63 | 45 | 71 | 54 | drug
June-05 | 86 | 65 | 46 | 72 | 56 | drug
June-12 | 88 | 66 | 48 | 72 | 57 | drug
June-19 | 90 | 68 | 50 | 72 | 59 | drug
June-26 | 92 | 68 | 50 | 72 | 60 | drug
July-03 | 104 | 76 | 51 | 72 | 63 | drug
July-10 | 117 | 81 | 52 | 90 | 67 | drug
May-08 | 1 | 24 | 20 | 6 | 51 | refusals
May-15 | 0 | 40 | 10 | 1 | 51 | refusals
May-22 | 7 | 0 | 5 | 0 | 12 | refusals
May-29 | 0 | 0 | 3 | 0 | 3 | refusals
June-05 | 0 | 3 | 1 | 0 | 4 | refusals
June-12 | 1 | 3 | 7 | 2 | 13 | refusals
June-19 | 1 | 2 | 2 | 0 | 5 | refusals
June-26 | 0 | 0 | 0 | 1 | 1 | refusals
July-03 | 0 | 5 | 1 | 0 | 6 | refusals
July-10 | 0 | 1 | 2 | 0 | 3 | refusals

## pediatric
status | Target | Reached | pct
Pre consent | 597 | 561 | 93.97%
1st support call | 561 | 537 | 95.72%
2nd support call | 537 | 521 | 97.02%
3rd support call | 521 | 500 | 95.97%
>3 support call | 500 | 387 | 77.4%

## main
reason | pct
She is adherent and doesn't need reminders | 31
The call takes a long time | 13
Shares phone and doesn't think it's safe to receive VMM | 12
Lack of disclosure of serostatus | 10
Lack of private space to receive VMM | 10
Fear, the partner does not allow to answer calls | 8
MM did not explain well the importance of VMM | 7
Only have time at night or weekend | 6
Shame | 1
Did not understand the importance of virtual tracking | 1

## weekly_plan
province | period | Target | OutCome
Cabo Delgado | May 04-08 | 99 | 94
Cabo Delgado | May 11-15 | 94 | 63
Cabo Delgado | May 18-22 | 112 | 65
Cabo Delgado | May 25-29 | 73 | 73
Cabo Delgado | June 1-5 | 97 | 67
Cabo Delgado | June 8-12 | 69 | 69
Cabo Delgado | June 15-19 | 94 | 94
Cabo Delgado | June 22-26 | 100 | 100
Cabo Delgado | June 29 - July 03 | 124 | 124
Cabo Delgado | July 06 - 10 | 123 | 116
Nampula | May 04-08 | 1012 | 860
Nampula | May 11-15 | 1202 | 1002
Nampula | May 18-22 | 1019 | 1016
Nampula | May 25-29 | 1220 | 1099
Nampula | June 1-5 | 1028 | 1025
Nampula | June 8-12 | 1247 | 1238
Nampula | June 15-19 | 1295 | 1211
Nampula | June 22-26 | 1152 | 915
Nampula | June 29 - July 03 | 1241 | 1199
Nampula | July 06 - 10 | 1298 | 1193
Zambézia | May 04-08 | 1400 | 814
Zambézia | May 11-15 | 1350 | 250
Zambézia | May 18-22 | 1300 | 860
Zambézia | May 25-29 | 1400 | 916
Zambézia | June 1-5 | 1350 | 866
Zambézia | June 8-12 | 1300 | 960
Zambézia | June 15-19 | 1400 | 877
Zambézia | June 22-26 | 1350 | 769
Zambézia | June 29 - July 03 | 1300 | 1008
Zambézia | July 06 - 10 | 1350 | 997
Matola-II | May 04-08 | 219 | 198
Matola-II | May 11-15 | 200 | 168
Matola-II | May 18-22 | 225 | 68
Matola-II | May 25-29 | 119 | 89
Matola-II | June 1-5 | 209 | 118
Matola-II | June 8-12 | 200 | 144
Matola-II | June 15-19 | 250 | 218
Matola-II | June 22-26 | 208 | 200
Matola-II | June 29 - July 03 | 197 | 172
Matola-II | July 06 - 10 | 216 | 210
m2m Moz | May 04-08 | 2730 | 1966
m2m Moz | May 11-15 | 2846 | 1483
m2m Moz | May 18-22 | 2656 | 2009
m2m Moz | May 25-29 | 2812 | 2177
m2m Moz | June 1-5 | 2684 | 2076
m2m Moz | June 8-12 | 2816 | 2411
m2m Moz | June 15-19 | 3039 | 2400
m2m Moz | June 22-26 | 2810 | 1984
m2m Moz | June 29 - July 03 | 2862 | 2503
m2m Moz | July 06 - 10 | 2987 | 2516

## global
status | period | Target | Outcome | pct
VMM Services | MM Trained | 278 | 278 | 100%
VMM Services | Pre-consent calls | 6563 | 5643 | 85.98%
VMM Services | 1st Support Calls | 5643 | 5252 | 93.07%
VMM Services | 2nd Support Calls | 5252 | 5098 | 97.07%
VMM Services | 3rd Support Calls | 5098 | 5024 | 98.55%
VMM Services | >3 Support Calls | 5024 | 6304 | 125.5%
VMM Services | Quarterly ARV refill | 15223 | 10169 | 66.8%
Weekly Plan | May 04-08 | 2730 | 1966 | 72.01%
Weekly Plan | May 11-15 | 2846 | 1483 | 52.11%
Weekly Plan | May 18-22 | 2656 | 2009 | 75.64%
Weekly Plan | May 25-29 | 2812 | 2177 | 77.42%
Weekly Plan | June 1-5 | 2684 | 2076 | 77.35%
Weekly Plan | June 8-12 | 2816 | 2411 | 85.62%
Weekly Plan | June 15-19 | 3039 | 2400 | 78.97%
Weekly Plan | June 22-26 | 2810 | 1984 | 70.6%
Weekly Plan | June 29 - July 03 | 2862 | 2503 | 87.46%
Weekly Plan | July 06 - 10 | 2987 | 2516 | 84.23%

## global (2)
status | period | OutCome | Target | pct
VMM Services | MM Trained | 278 | 278 | 100%
VMM Services | Pre-consent calls | 5440 | 6904 | 78.79%
VMM Services | 1st Support Calls | 5042 | 5361 | 94.05%
VMM Services | 2nd Support Calls | 4751 | 5042 | 94.23%
VMM Services | 3rd Support Calls | 4532 | 4751 | 95.39%
VMM Services | >3 Support Calls | 4291 | 4532 | 94.68%
VMM Services | Quarterly ARV refill | 9220 | 15495 | 59.5%
Weekly Plan | May 04-08 | 1966 | 2730 | 72.01%
Weekly Plan | May 11-15 | 1483 | 2846 | 52.11%
Weekly Plan | May 18-22 | 2009 | 2656 | 75.64%
Weekly Plan | May 25-29 | 2177 | 2812 | 77.42%
Weekly Plan | June 1-5 | 2076 | 2684 | 77.35%
Weekly Plan | June 8-12 | 2411 | 2816 | 85.62%
Weekly Plan | June 15-19 | 2400 | 3039 | 78.97%
Weekly Plan | June 22-26 | 1984 | 2810 | 70.6%
Weekly Plan | June 29 - July 03 | 2503 | 2862 | 87.46%
|  | period |  | MM Trained |  | Pre-consent calls | 1st Support Calls | 2nd Support Calls | 3rd Support Calls | >3 Support Calls | Quarterly ARV refill
|  | Target |  | 278 |  | 6904 | 5361 | 5042 | 4751 | 4532 | 15495
|  | OutCome |  | 278 |  | 5440 | 5042 | 4751 | 4532 | 4291 | 9220
|  | pct |  | 1 |  | 0.78795 | 0.9405 | 0.94228 | 0.9539 | 0.94682 | 0.59503
|  | May 04-08 |  | May 11-15 |  | May 18-22 | May 25-29 | June 1-5 | June 8-12 | June 15-19 | June 22-26
|  | 2730 | Target | 2846 |  | 2656 | 2812 | 2684 | 2816 | 3039 | 2810
|  | 1966 | OutCome | 1483 |  | 2009 | 2177 | 2076 | 2411 | 2400 | 1984
|  | 72.01% | pct | 52.11% |  | 75.64% | 77.42% | 77.35% | 85.62% | 78.97% | 70.6%
|  |  |  | May-08 | 2 | 24 | 92 | 17 | 135 | refusals
|  |  |  | May-15 | 2 | 40 | 92 | 17 | 151 | refusals
|  |  |  | May-22 | 9 | 40 | 54 | 18 | 121 | refusals
|  |  |  | May-29 | 9 | 40 | 57 | 18 | 124 | refusals
|  |  |  | June-05 | 9 | 40 | 57 | 14 | 120 | refusals
|  |  |  | June-12 | 10 | 40 | 64 | 11 | 125 | refusals
|  |  |  | June-19 | 10 | 40 | 64 | 11 | 125 | refusals
|  |  |  | June-26 | 0 | 0 | 0 | 0 | 0 | refusals
|  |  |  | July-03 | 0 | 3 | 1 | 0 | 4 | refusals
|  |  |  | July-10 | 0 | 3 | 2 | 0 | 5 | refusals